## sprint plan
Year
Month | [19 empty] | 2019-10-01
CW | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | # sprint | Mo | Tu | We | Th | Fr | Sa | Su | Notes
SW |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | free | time |  |  |  | 2
sprint |  |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 | [8 empty] | 9
[6 empty] | del 1 |  |  | del2 |  |  | del3 |  |  |  | del4 | [5 empty] | 16
23
30
2019-11-01
6
13
20
27
2019-12-01
4
11
18
Meetings time 14:30- 15:00
Project Calendar 19/20
September
October
November
December
January
Meetings Date Memo active date ==

## sprint1
|  | Sprint Backlog of Sprint 1 |  |  | del date == 09/10/19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Goals | My Tasks
0 | Domain model | Domain model | High |  |  | done | Stakeholders | A list of stakeholsers.
1 | Documentation | Initial structure of main document. | High |  |  | done | To think about and articulate first and most important user stories; | An initial set of user sotries.
2 | User stories | Write some user stories. | High |  |  | done | Domain model | A user case diagram -> del 2
4 | Vision | Make Vision of project. | High |  |  | done | Product Backlog(PL) | A domain model.
5 | Infrastructure | Set up infrastructure Gitlab | High |  | 0.5h | done | Organize my sprint | Set up my personal environment
6 | User Stories | Define user stories and enter them to the main document. | High |  |  | in process | fix the list of PB items for this sprint | Establish a new Git branch
7 | User Stories | Extend user stories with "success" and "failure" | High |  |  | in process | split PB items into tasks | Provide initial classes. -> del2
8 | Infrastructure | Sprint Backlog. Make a document with sprint planning. Divide work in 14 weeks . | High |  |  | almost done |  | Provide tests for my clssses. -> del2
9 | Documentation | Extend documentation with explanation about Angular and Spring. "What is it Spring, Angular …."
10 | Documentation | Make clear vision document and put it to the main document | High |  |  | in process
11 | Start project | Start a project. Start firsts classes | Low |  |  | in process

## spr2
|  | Sprint Backlog of Sprint 2 |  |  | del date == 30/10/19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Goals | My Tasks
12 | Domain Classes | Develop sketch of working domain classes | High |  |  |  |  | Organize your sprint
13 | Unit tests | Develop unit tests for domain model | High |  |  |  |  | Fix the list of PB items for this sprint
14 | Javadoc | Ajust test classes | High |  |  |  |  | Split larger PB items into tasks
15 | Postgres SQL | Add postgress SQL to the project, make connection | High
16 | User Story | Implement services for each entity classes | High |  |  |  |  | Update any documents you have so far, if needed
17 | User Story | Implement participant controller | Low |  |  |  |  | Provide code for selected user stories (or parts thereof)
Production Java interfaces and classes
(Initial) object persistence via Java's persistence API (JPA).
Start Angular
JUnit test classes
Components of this Deliverable
The deliverable for this sprint shall encompass:
Production Java interfaces and classes
JavaDoc documentation for public methods of entities and controllers
JUnit test classes,

## spr3
del date == 20/11/19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint4
[5 empty] | del date == 18/12/19 |  | ? Not sure
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint5
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## rules
Important
1 | Make a commit oft, so the supervisor can be better inform about actual state of work.
2 | Make java docs and tests.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21