## rules
Important
1 | Make a commit oft, so the supervisor can be better inform about actual state of work.
2 | Make java docs and tests.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## spr3->09.10.19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned
0 | Infrastructure | Set up infrastructure Gitlab | High | 1 h | 1h
1 | User Stories | Define user stories and enter them to the main document into product backlog | High | 2h | 10h
2 |  | Extend user stories with "success" and "failure" |  | 2h
3 | Infrastructure | Sprint Backlog. Make a document with sprint planning. Divide work in 14 weeks . | High | 1 h | 1 h
4 |  | Exted ducumentatin with explanation about Angular and Spring. "What is it Spring, Angular …."
5 |  | Start a project. Start firsts classes

## spr4->16.10.19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint5
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint6
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned