## rules
Important
1 | Make a commit oft, so the supervisor can be better inform about actual state of work.
2 | Make java docs and tests.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## sprint1
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned
0 | Domain model | Domain model | High |  |  | done
1 | Documentation | Initial structure of main document. | High |  |  | done
2 | User stories | Write some user stories. | High |  |  | done
4 | Vision | Make Vision of project. | High |  |  | done

## spr2->09.10.19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned
5 | Infrastructure | Set up infrastructure Gitlab | High |  | 0.5h | done
6 | User Stories | Define user stories and enter them to the main document. | High |  |  | in process
7 | User Stories | Extend user stories with "success" and "failure" | High |  |  | in process
8 | Infrastructure | Sprint Backlog. Make a document with sprint planning. Divide work in 14 weeks . | High |  |  | in process
9 | Documentation | Extend documentatin with explanation about Angular and Spring. "What is it Spring, Angular …."
10 | Documentation | Make clear vision document and put it to the main document | High |  |  | in process
11 | Start project | Start a project. Start firsts classes | Low |  |  | in process

## spr3->16.10.19
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint4
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned

## sprint5
Id | Story Name | Story Description | Priority | Estimated Effort | Actual Effort | Status | Owner | lesson learned